## 0_Government_Dashboard
SAMPLE GOVERNMENT STARTUP FUNDING DASHBOARD
Funding Requested | ₹50,00,000 | What Government Will Expect
Founder Contribution | ₹10,00,000 | • A clearly defined problem and measurable baseline
Total Project Cost | ₹60,00,000 | • A working prototype/MVP, not only an idea
Pilot Duration | 6 months | • A credible team capable of execution
Pilot Departments | 2 | • Detailed milestone-based budget
Target Startups Evaluated | 50 | • Pilot plan with named government stakeholders
Target Pilots | 5 | • Security, privacy and legal readiness
Target User Satisfaction | 4/5+ | • Transparent KPI measurement
• Monthly financial and progress reporting
• Evidence that the solution can scale
• A clear post-pilot procurement/adoption path

## 1_Project Overview
Field | Sample Response
Applicant | Example Innovations Pvt. Ltd.
Problem | Government departments struggle to discover, validate, pilot and scale startup solutions for local problems.
Proposed Solution | A digital platform for problem discovery, startup matching, technical evaluation, pilot management, outcome tracking and scale-up.
Primary Users | State departments, municipal corporations, district administrations, government agencies, startups and evaluators
Pilot Geography | Pune + Nashik (sample)
Pilot Duration | 6 months
Funding Requested | ₹50,00,000
Founder Contribution | ₹10,00,000
Total Project Cost | ₹60,00,000
Expected Government Outcome | Faster discovery of credible solutions, transparent pilot evaluation and evidence-based procurement/scale-up.
Government Ask | Grant + access to pilot departments/data + designated nodal officer + pilot approvals

## 2_Proposal Checklist
Section | What Government Needs From You | Sample Evidence | Status | Owner
Problem Definition | Clear problem, affected population, geography and current cost/impact | Baseline report + government stakeholder interviews | Ready | Founder
Solution | How the product solves the problem and why existing systems are insufficient | Architecture + clickable prototype | Ready | CTO
Innovation | Technical/operational differentiation | AI matching model + evaluation engine | In Progress | CTO
Market/Government Fit | Who will use/pay and how adoption happens | Letters of intent / department interest | In Progress | CEO
Pilot Plan | Location, scope, timeline, users, success criteria | 6-month pilot plan | Ready | PM
Team | Founder/team capability and relevant experience | CVs + role matrix | Ready | CEO
Budget | Detailed use of grant and co-funding | Milestone-linked budget | Ready | Finance
Compliance | Company, tax, IP, data protection, security and procurement readiness | Certificates + policies | In Progress | Compliance
Impact Measurement | KPIs and baseline vs target | KPI dashboard specification | Ready | Data Lead
Scale Plan | How pilot becomes statewide deployment | District rollout plan | In Progress | CEO

## 3_Team
Person | Role | Key Responsibility | Relevant Experience | Full-time? | Monthly Cost (₹) | Evidence
Aarav Shah | CEO/Founder | Government partnerships, product strategy | 5 years startup/product experience | Yes | 120000 | CV + founder profile
Riya Mehta | CTO | Platform, AI matching, cybersecurity | 6 years software/AI | Yes | 150000 | CV + GitHub/portfolio
Kabir Joshi | Product Manager | Pilot execution and department coordination | 4 years GovTech/product | Yes | 100000 | CV
Neha Patil | Data Lead | KPI framework, analytics and reporting | 3 years data analytics | Yes | 90000 | CV
External Advisor | GovTech Advisor | Procurement and implementation guidance | Former public-sector program experience | Part-time | 50000 | Engagement letter

## 4_Budget
Category | Expense | Amount (₹) | % of Project | Justification
Personnel | Engineering salaries | 1800000 | 30% | Required to deliver the sample pilot
Personnel | Product + project management | 900000 | 15% | Required to deliver the sample pilot
Technology | Cloud, AI APIs, hosting, monitoring | 600000 | 10% | Required to deliver the sample pilot
Technology | Cybersecurity audit + penetration testing | 400000 | 7% | Required to deliver the sample pilot
Pilot | Department onboarding, field deployment, training | 500000 | 8% | Required to deliver the sample pilot
Pilot | Travel and field operations | 300000 | 5% | Required to deliver the sample pilot
Hardware | Sample IoT/edge devices for pilot | 400000 | 7% | Required to deliver the sample pilot
Legal/Compliance | Company, contracts, privacy, IP and audit | 250000 | 4% | Required to deliver the sample pilot
Research | Baseline study + impact evaluation | 300000 | 5% | Required to deliver the sample pilot
Contingency | Unexpected pilot/technical costs | 550000 | 9% | Required to deliver the sample pilot
TOTAL |  | 6000000

## 5_Milestones
Milestone | Timeline | Deliverable | Government Release (₹) | Acceptance Criteria | Evidence
M1: Discovery | Month 1 | Problem validation + pilot department MoUs | 1000000 | 2 departments formally onboarded | MoU + discovery report
M2: MVP | Month 2 | Working platform with startup registry and problem portal | 1000000 | Core workflows functional | Demo + test report
M3: Evaluation Engine | Month 3 | Scoring, due diligence and matching module | 1000000 | Evaluation completed for 20 sample startups | Evaluation report
M4: Pilot | Months 4-5 | Live pilot with departments | 1500000 | At least 10 solutions evaluated; 3 pilots initiated | Pilot dashboard
M5: Impact & Scale | Month 6 | Impact report + statewide scale plan | 500000 | Targets met and scale recommendation submitted | Independent/department validation

## 6_KPIs
KPI | Baseline | 6-Month Target | How Measured | Government Value | Sample Result
Average time to identify potential solution | 45 days | 15 days | Platform timestamps | Faster problem solving | 12 days
Startups evaluated | 0 | 50 | Platform records | Larger solution pool | 58
Solutions shortlisted | 0 | 15 | Evaluation score | Better selection | 17
Pilots launched | 0 | 5 | Pilot contracts/MoUs | Evidence before scale | 5
Pilot success rate | N/A | 70%+ | Predefined KPI score | Lower procurement risk | 80%
Government user satisfaction | N/A | 4/5+ | Survey | Adoption | 4.4/5
Estimated cost/time saved | N/A | ₹25 lakh / year | Validated calculation | Public money efficiency | ₹31 lakh

## 7_Technical_Requirements
Area | What You Need to Provide | Sample Specification | Evidence
Architecture | System architecture and deployment model | Cloud-native web platform + API layer | Architecture diagram
Security | Security controls and audit plan | RBAC, encryption, logs, backups, VAPT | Security checklist + audit
AI/ML | Explainable matching/evaluation methodology | Problem-to-startup matching + weighted scoring | Model card + test results
Data | Data sources and ownership | Government-provided datasets + startup-submitted data | Data inventory
Availability | Reliability target | 99.5% during pilot | Monitoring report
Scalability | Statewide expansion readiness | District/department multi-tenant architecture | Load test
Accessibility | Usable by government staff | Responsive UI + Marathi/English support | Accessibility test

## 8_Compliance
Requirement | What You Should Have | Sample Status | Document/Evidence
Legal entity | Company incorporation/registration | Ready | Certificate of incorporation
Tax | PAN/TAN/GST as applicable | Ready | Certificates
Banking | Dedicated company bank account | Ready | Cancelled cheque/bank letter
IP ownership | Founder/company ownership of software/IP | In Progress | IP assignment + declaration
Data protection | Privacy policy, data processing controls | In Progress | Privacy/data policy
Cybersecurity | VAPT/security audit plan | In Progress | Audit quotation/report
Government contracts | Pilot MoU + data-sharing + SLA templates | In Progress | Draft agreements
Conflict of interest | Founder/team declarations | Ready | Signed declarations
Financial reporting | Grant utilization and accounting process | Ready | Monthly expense register

## 9_Pilot_Plan
Pilot Area | Government Problem | Solution Module | Users | Duration | Success Metric | Sample Target
Pune Municipal Corporation | Slow discovery of technology solutions | Problem portal + startup matching | 20 officers | 12 weeks | Time from problem to shortlist | <15 days
Nashik District | Difficulty validating startup claims | Due diligence + pilot scoring | 10 officers + evaluators | 12 weeks | Solutions independently scored | 20
State-level demo | No common view of pilot outcomes | Impact dashboard | State program team | 4 weeks | Pilots with quantified outcomes | 5

## 10_Risk_Register
Risk | Probability | Impact | Mitigation | Owner | Trigger/Indicator
Government approvals delayed | Medium | High | Nominate nodal officer; approval calendar | CEO | No approval within 10 working days
Low startup participation | Medium | Medium | Outreach via incubators and startup networks | Growth Lead | <20 applications in first month
Poor data quality | High | High | Data validation + manual review | Data Lead | >10% invalid records
Cybersecurity incident | Low | Very High | VAPT, least privilege, monitoring, backups | CTO | Critical security alert
Pilot does not show measurable impact | Medium | High | Define baseline and KPIs before deployment | PM | KPI <70% of target

## 11_Monthly_Report
Month | Grant Received (₹) | Amount Spent (₹) | Cumulative Spend (₹) | Milestone Status | Key Output | Issues | Next Month
Month 1 | 1000000 | 850000 | 850000 | On track | 2 pilot departments onboarded | Data access pending | Complete MVP
Month 2 | 1000000 | 950000 | 1800000 | On track | MVP launched | Minor UX issues | Evaluation engine
Month 3 | 1000000 | 980000 | 2780000 | On track | 20 startups evaluated | None | Launch live pilot
Month 4 | 750000 | 700000 | 3480000 | On track | 3 pilots initiated | Training schedule | Expand pilot
Month 5 | 750000 | 720000 | 4200000 | On track | 5 pilots active | None | Impact evaluation
Month 6 | 500000 | 450000 | 4650000 | Complete | Impact report + scale plan | None | Statewide rollout proposal

## 12_Final_Submission_Checklist
Item | Required? | Sample File/Proof | Status
Pitch deck | Yes | 10–15 slide investor/government deck | Ready
Detailed project proposal | Yes | 20–30 page proposal | Ready
Product demo | Yes | Live URL + demo video | In Progress
Prototype/source code | Usually | Git repository + deployment | In Progress
Detailed budget | Yes | Milestone-linked budget | Ready
Founder/team CVs | Yes | Signed CVs | Ready
Company documents | Yes | Incorporation, PAN, GST as applicable | Ready
Bank details | Yes | Company account proof | Ready
IP declaration | Yes | Ownership/assignment documents | In Progress
Data/security plan | Yes for a GovTech pilot | Privacy + security architecture | In Progress
Pilot MoU/LOI | Strongly recommended | Department/institution letter | In Progress
Baseline study | Yes | Current-state measurements | Ready
KPI framework | Yes | Targets + measurement method | Ready
Procurement/scale plan | Yes | How government can adopt after pilot | Ready
Grant utilization reporting | Yes | Monthly expense + utilization certificate | Ready